## Gantt
Baja SAE – Controls ¦ Capstone Project Gantt Chart
Project start (Mon): |  | 2026-08-31 |  | Today: | 2026-10-02
Edit the yellow columns (Task, Type, Start, End). Days, phase roll-ups and the bars update automatically. Insert new rows inside a phase to add tasks (copy a row first to keep its formulas).
Legend: | [7 empty] | Deliverable |  |  |  |  | Task |  |  |  |  | Milestone ◆ |  |  |  |  | Phase summary |  |  |  |  | Break
[7 empty] | Aug | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr
[6 empty] | Course week → | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Break | Break | Break | Break | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | Break | 24 | 25 | 26 | 27 | 28 | 29 | 30
ID | Phase / Module | Task / Deliverable | Type | Start | End / Due | Days | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26
|  | Pre-Project | Phase | 2026-08-31 | 2027-04-25 | 238
M00 | Course Overview | Capstone Assignment of Ownership & NDA | Deliverable | 2026-08-31 | 2026-09-13 | 14
M01 | Design Process | Team Identity and Contract | Deliverable | 2026-09-14 | 2026-09-20 | 7
TR/WTM | Weekly | Time reporting (TR1–TR25) & weekly team meetings | Recurring | 2026-09-14 | 2027-04-25 | 224
|  | Preliminary Design Phase | Phase | 2026-09-21 | 2026-11-08 | 49
M02 | Voice of the Customer | Voice of the Customer | Deliverable | 2026-09-21 | 2026-09-27 | 7
M03 | Project Definition | Project GANTT Chart | Deliverable | 2026-09-28 | 2026-10-04 | 7
M04 | Problem Definition | Statement of Work (SOW) | Deliverable | 2026-10-05 | 2026-10-11 | 7
PE1 | Problem Definition | 1st Peer Evaluation & Team Retrospective | Milestone | 2026-10-11 | 2026-10-11 | 1 | [5 empty] | ◆
M05 | Concept Generation | Concept Portfolio | Deliverable | 2026-10-12 | 2026-10-25 | 14
M06 | Proof of Concept | Proof of Concept Demonstration Video | Deliverable | 2026-10-19 | 2026-10-25 | 7
M07 | Concept Evaluation | Preliminary Design Review (PDR) | Deliverable | 2026-10-26 | 2026-11-08 | 14
|  | Product Design Phase | Phase | 2026-11-09 | 2026-12-13 | 35
PE2 | Product Design | 2nd Peer Evaluation & Team Retrospective | Milestone | 2026-11-15 | 2026-11-15 | 1 | [10 empty] | ◆
M08a | Product Design | Performance Review, Drawing Package & Budget | Deliverable | 2026-11-09 | 2026-12-06 | 28
M08b | Product Design | Updated SOW | Deliverable | 2026-11-09 | 2026-12-06 | 28
M08c | Product Design | Critical Design Review (CDR) | Deliverable | 2026-11-09 | 2026-12-06 | 28
BLD | Product Design | Finalize design, order parts, start building | Task | 2026-12-07 | 2026-12-13 | 7
PE3 | Product Design | 3rd Peer Evaluation & Team Retrospective | Milestone | 2026-12-13 | 2026-12-13 | 1 | [14 empty] | ◆
|  | Final Design Phase | Phase | 2027-01-11 | 2027-05-02 | 112
M09 | 1st Product Build/Test | 1st Deliverable Demonstration Video | Deliverable | 2027-01-11 | 2027-02-14 | 35
PE4 | 1st Product Build/Test | 4th Peer Evaluation & Team Retrospective | Milestone | 2027-02-14 | 2027-02-14 | 1 | [23 empty] | ◆
M10 | 2nd Product Build/Test | 2nd Deliverable Demonstration Video | Deliverable | 2027-02-15 | 2027-03-28 | 42
PE5 | 2nd Product Build/Test | 5th Peer Evaluation & Team Retrospective | Milestone | 2027-03-28 | 2027-03-28 | 1 | [29 empty] | ◆
M11a | Product Documentation | Finalize Product | Task | 2027-03-29 | 2027-04-25 | 28
M11b | Product Documentation | Final Design Report | Deliverable | 2027-03-29 | 2027-05-02 | 35
M11c | Product Documentation | Senior Design Night Poster | Deliverable | 2027-03-29 | 2027-05-02 | 35
M11d | Product Documentation | Capstone Closeout | Deliverable | 2027-03-29 | 2027-05-02 | 35
M11e | Product Documentation | Senior Exit Survey | Deliverable | 2027-03-29 | 2027-05-02 | 35
PE6 | Product Documentation | 6th Peer Evaluation | Milestone | 2027-05-02 | 2027-05-02 | 1 | [34 empty] | ◆
SDN | Product Documentation | Senior Design Night (date TBD – enter when announced) | Milestone
|  | Additional Items (add your own tasks here) | Phase | 2026-10-01 | 2027-04-29 | 211
AdI01 | Individual Trainings | Metal Factory Permits (Blue, Red, Green) | Deliverable | 2026-10-01 | 2026-10-31 | 31
AdI02 | Individual Trainings | Welding Training | Task | 2026-10-31 | 2026-11-14 | 15
AdI03 | Parts Deadline | Part Selection Deadline | Milestone | 2027-02-01 | 2027-02-01 | 1 | [22 empty] | ◆
AdI04 | Parts Deadline | Off-the-shelf Part Deadline | Milestone | 2027-03-01 | 2027-03-01 | 1 | [26 empty] | ◆
TST0 | Testing | Testing phase begins (1 month before race) | Milestone | 2027-03-29 | 2027-04-29 | 32 | [34 empty] | ◆
RACE | Competition | Baja SAE Race Day | Milestone | 2027-04-29 | 2027-04-29 | 1 | [34 empty] | ◆
Notes: Due dates assume each deliverable is due the Sunday ending its module's last week — adjust to the actual Canvas due dates. Course week 22 is listed as "Feb 23 – Feb 28" in the syllabus; treated here as Feb 22 – 28.
Source: course schedule & Baja SAE – Controls milestone list (provided by Alex). Race day (Apr 29) and testing-phase start (one month prior) per Alex.
Note on C2: Week 1 start date from the course schedule (Mon Aug 31, 2026). Timeline headers are calculated from this.

## Course Schedule
Capstone Course Schedule (2026–27)
Week | Start | End | Module | Time Report | Team Meeting | Peer Eval / Retro | Deliverable(s)
1 | 2026-08-31 | 2026-09-06 | M00 – Course Overview | – | – | –
2 | 2026-09-07 | 2026-09-13 | M00 – Course Overview | – | – | – | Capstone Assignment of Ownership & NDA
3 | 2026-09-14 | 2026-09-20 | M01 – Overview of the Design Process | TR1 | WTM1 | – | Team Identity and Contract
4 | 2026-09-21 | 2026-09-27 | M02 – Voice of the Customer | TR2 | WTM2 | – | Voice of the Customer
5 | 2026-09-28 | 2026-10-04 | M03 – Project Definition | TR3 | WTM3 | – | GANTT Chart
6 | 2026-10-05 | 2026-10-11 | M04 – Problem Definition | TR4 | WTM4 | 1st Peer Eval & Retro | Statement of Work (SOW)
7 | 2026-10-12 | 2026-10-18 | M05 – Concept Generation | TR5 | WTM5 | –
8 | 2026-10-19 | 2026-10-25 | M06 – Proof of Concept | TR6 | WTM6 | – | Concept Portfolio; Proof of Concept Demo Video
9 | 2026-10-26 | 2026-11-01 | M07 – Concept Evaluation | TR7 | WTM7 | –
10 | 2026-11-02 | 2026-11-08 | M07 – Concept Evaluation | TR8 | WTM8 | – | Preliminary Design Review
11 | 2026-11-09 | 2026-11-15 | M08 – Product Design | TR9 | WTM9 | 2nd Peer Eval & Retro
12 | 2026-11-16 | 2026-11-22 | M08 – Product Design | TR10 | WTM10 | –
13 | 2026-11-23 | 2026-11-29 | M08 – Product Design | – | – | –
14 | 2026-11-30 | 2026-12-06 | M08 – Product Design | TR11 | WTM11 | – | Performance Review; Updated SOW; Drawing Package & Budget; Critical Design Review
15 | 2026-12-07 | 2026-12-13 | (Finalize design) | – | – | 3rd Peer Eval & Retro | Finalize Design, Order Parts, Start Building
WINTER BREAK
16 | 2027-01-11 | 2027-01-17 | M09 – 1st Product Build/Test | TR13 | WTM13 | –
17 | 2027-01-18 | 2027-01-24 | M09 – 1st Product Build/Test | TR14 | WTM14 | –
18 | 2027-01-25 | 2027-01-31 | M09 – 1st Product Build/Test | TR15 | WTM15 | –
19 | 2027-02-01 | 2027-02-07 | M09 – 1st Product Build/Test | TR16 | WTM16 | –
20 | 2027-02-08 | 2027-02-14 | M09 – 1st Product Build/Test | TR17 | WTM17 | 4th Peer Eval & Retro | 1st Deliverable Demo Video
21 | 2027-02-15 | 2027-02-21 | M10 – 2nd Product Build/Test | TR18 | WTM18 | –
22 | 2027-02-22 | 2027-02-28 | M10 – 2nd Product Build/Test | TR19 | WTM19 | –
23 | 2027-03-01 | 2027-03-07 | M10 – 2nd Product Build/Test | TR20 | WTM20 | –
SPRING BREAK
24 | 2027-03-15 | 2027-03-21 | M10 – 2nd Product Build/Test | TR21 | WTM21 | –
25 | 2027-03-22 | 2027-03-28 | M10 – 2nd Product Build/Test | TR22 | WTM22 | 5th Peer Eval & Retro | 2nd Deliverable Demo Video
26 | 2027-03-29 | 2027-04-04 | M11 – Product Documentation | TR23 | WTM23 | –
27 | 2027-04-05 | 2027-04-11 | M11 – Product Documentation | TR24 | WTM24 | –
28 | 2027-04-12 | 2027-04-18 | M11 – Product Documentation | TR25 | WTM25 | –
29 | 2027-04-19 | 2027-04-25 | M11 – Product Documentation | TR26 | WTM26 | –
30 | 2027-04-26 | 2027-05-02 | M11 – Product Documentation | – | – | 6th Peer Eval | Baja SAE Race Day (Apr 29); Finalize Product; Final Design Report; Senior Design Night Poster; Capstone Closeout; Senior Exit Survey
SENIOR DESIGN NIGHT – TBD
Deliverables are listed in the last week of their module. Week 22 shown as Feb 22–28 (syllabus lists Feb 23–28).